## Sheet1
Tester Name | Kaustubh Gurav
Project Name | CV Generator
Module | Feature | Testing Type | Execution Start Date | Execution End Date | Build ID/Name | Test Environment | Sprint | Total no. of test cases/scenarios | Total no. of test cases/scenarios executed | Total no. of test cases not executed | Total no. test cases/scenarios PASS | Total no. test cases/scenarios FAIL | % PASS | % FAIL | Comment
Dashboard |  | Functional | 2023-02-04 | 2023-02-05 |  |  |  | 9 | [5 empty] | #DIV/0! | Due to blocker bug not able to execute the scenarios
Feed Data |  | Functional | 2023-02-04 | 2023-02-05 |  |  |  | 24 | [6 empty] | Due to blocker bug not able to execute the scenarios
Generate CV |  | Functional | 2023-02-04 | 2023-02-05 |  |  |  | 12 | [6 empty] | Due to blocker bug not able to execute the scenarios
Project API |  | API | 2023-02-04 | 2023-02-05 |  |  |  | 6 | 6 | 0 | 5 | 1 | 83.33% | 16.67%
Technical skills API |  | API | 2023-02-04 | 2023-02-05 |  |  |  | 6 | [6 empty] | Due to blocker bug not able to execute the scenarios